## Allergy BeGone-Site development
Allergy BeGone - Work Progress Report
S.No. | Task | Subtask | Comments | Status |  | Items reqd. from client end
1 | Improved Control over Category URLs for SEO | make SEO Friendly URL |  | done | Verified
2 | related products | - to show other products on the webpage that are related (accessories or otherwise) |  | done | Verified
3 | page checkout- 1 step checkout |  |  | done | Verified
4 | blog integration- | not sure which one. would like to have it at tail of domain not subdomain (if possible) integrate wordpress blog with magento using plugin |  | done
5 | tier prices- |  |  | done
6 | mobile theme and checkout |  |  | done | Verified
7 | socialmedia buttons | social sharing and follow button |  | done | Not available
8 | Pagination (items that are not ordereable do not show up on pages, only show up in search) |  |  | done | Not available
9 | Products Tabs extension - for tabbed browsing on items |  |  | done | Redo
10 | multi image, zoom on image (magic zoom or other) | install free product zoom plugin |  | done | Not available
11 | Magento Setup (front end, backend, db etc) |  |  | done | Verified
12 | Theme Integration |  |  | done | Verified
13 | google trusted store | http://www.magentocommerce.com/magento-connect/google-trusted-stores.html |  | done |  | To earn the badge, your store must demonstrate fast, reliable shipping and responsive customer service. If you meet the program criteria, visitors to your site will see the Google Trusted Store badge and can hover over it to view a report card showing your store’s performance metrics.
14 | dropship360- would currently like a way to automatically export dropship orders | http://www.magentocommerce.com/magento-connect/dropship360.html |  | done |  | Logicbroker subscription and account
15 | livechat | add 3rd party chat tool |  | done | Not available
16 | product reviews |  |  | done | verified- Check for ratings | magento default reviews is done as well as amazon reviews. Star rating work is also done. We've used our amazon credentials for now, but need the client's amazon credentials for this work.
17 | inventory import - | we would provide a csv file from our host system, until you/we establish a better method. | We assume that you would provide us csv file having all product attributes in one single file. | pending |  | Some 1000 products imported
18 | tracking number import | customize the code to import the tracking number | We would want to know what all fields you need in csv file. | pending |  | This will be done once products are imported
19 | shipping rate tool- we currently use kingwebmaster advancedshippingmanager (need something similar) | shipping integration |  | in-progress |  | Could you send over current shipping details?
20 | Subscribe and save- Recurring orders |  |  | in-progress |  | Are you presently using recurring feature? If yes, can we get some details?
21 | delete orders |  |  | pending
22 | RMA |  |  | buy plugin |  | https://ecommerce.aheadworks.com/magento-extensions/rma.html
23 | abandoned carts closer- not specific to any app company | Required plugin or customization assuming client provide the plugin | We assume we are talking about customer abondoned carts here. | buy plugin |  | https://www.magentocommerce.com/magento-connect/abandoned-cart-alerts-pro.html
24 | Search Product | Improved search over standard product - we currently use nextopia | We can either integrate the same Nextopia or look for some other extension. Let us know if you are looking for anything specific to show up in search bar? | buy plugin |  | NEXTOPIA: https://www.magentocommerce.com/magento-connect/nextopia-search-connect.html OR SPHINX: https://mirasvit.com/magento-extensions/sphinx-search-ultimate.html
25 | Social Login | Install social login plugin (facebook/google/twitter) |  | pending |  | https://www.magentocommerce.com/magento-connect/social-login-20.html
26 | GiftWrap | Install Gift plugin |  | buy plugin |  | https://cmsideas.net/magento-gift-wrap.html
27 | Follow Up Email | http://www.magentocommerce.com/magento-connect/follow-up-email-by-aheadworks.html |  | buy plugin |  | https://www.magentocommerce.com/magento-connect/follow-up-email-by-aheadworks.html

## Backend Integration
S.No | Task | SubTask | Status | Comments
1 | Sync the Amazon Marketplace with ERP
a) |  | Read Order Information | Completed and tested in production server
b) |  | Update shipping information
2 | Sync the eBay Marketplace with ERP
a) |  | Read Order Information | Completed and tested in production server
b) |  | Update shipping information | Completed and tested in production server
3 | Sync the Magento Marketplace with ERP
a) |  | Read Order Information | Completed and tested in production server
b) |  | Update shipping information | Completed and tested in production server
4 | Integrate all the sync applications used for different marketplace integrations

## Clarifications
S.No | Clarification/Question | Resolution | Status | Comments
1 | Does all the marketplaces have the same formatting for the order and the shipping information?
2 | Do we write all the order information and read the shipping information in a single or individual files for each marketplace?
3 | What is the frequency in which the files would be read or updated?